## Dashboard
IFRS 18 Adoption — Project Plan Dashboard
288 - IFRS 18 ¦ Updated Jul 14, 2026
TOTAL EFFORT | DURATION | ACTIVITIES | GO-LIVE TARGET
~105 PD | ~22 weeks | 60 | 10 Nov 2026
was ~95 PD before SAP Note + Treasury review | mid-July to early December 2026 | across 8 phases | ahead of the 1 Jan 2027 effective date
Project Timeline
Effort Breakdown

## Project Plan
Activity ID | Exec. Order | Phase | Description | SAP Transaction(s) / Object(s) | GAP Ref | GAP Name | Gap Type | Role | Effort (PD) | Start Date | End Date | Duration (days) | Dependencies | Status
1.1 | 1 | 1 - Design & Preparation | Finalize IFRS 18 P&L category design with group accounting team (Operating/Investing/Financing boundaries, subtotal definitions) | Workshop - no transaction; output is a signed-off category definition document | All | Cross-cutting | - | FC + Accounting | 3 | 2026-07-14 | 2026-07-18 | 5 | - | Not Started
1.2 | 2 | 1 - Design & Preparation | Define new FSV hierarchy node structure for ZHFM, ZCPL, ZUKV (node IDs, parent-child relationships, G/L account assignments) | Design doc for later use in OB58 (Financial Statement Version: Maintain) | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC | 5 | 2026-07-14 | 2026-07-21 | 8 | - | Not Started
1.3 | 3 | 1 - Design & Preparation | Define new HFM structure positions and attribute flags (consolidation method, functional area, intercompany, movement type, region, sign reversal) | Design doc for later use in SM30 on table /FIT/FI_F_STRUCT | 2, 3 | GAP 2, GAP 3 | - | FC | 3 | 2026-07-19 | 2026-07-23 | 5 | 1.1 | Not Started
1.4 | 3 | 1 - Design & Preparation | Kick-off coordination with HFM team (new structure positions, receiving format) | Meeting - no transaction | 3 | Financial Data Extraction for Group Consolidation | INTERFACE, CONFIG | FC + HFM | 1 | 2026-07-21 | 2026-07-23 | 3 | - | Not Started
1.5 | 3 | 1 - Design & Preparation | Kick-off coordination with Tagetik team (account code alignment) | Meeting - no transaction | 7 | IFRS 16 Lease Accounting Data Loading | CONFIG | FC + Tagetik | 1 | 2026-07-21 | 2026-07-23 | 3 | - | Not Started
1.6 | 3 | 1 - Design & Preparation | Kick-off coordination with AMANA team (new category handling) | Meeting - no transaction | 4 | Financial Statement Data Export | INTERFACE | FC + AMANA | 0.5 | 2026-07-21 | 2026-07-23 | 3 | - | Not Started
1.7 | 1 | 1 - Design & Preparation | Review and implement SAP Note 3670330 - check validity for current release, review all child notes (3694359, 3696338, 3700153), implement corrections via SNOTE | SNOTE (Note Implementation) for Note 3670330 and its child notes | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | Basis + FC | 2 | 2026-07-14 | 2026-07-17 | 4 | - | Not Started
1.8 | 1 | 1 - Design & Preparation | Review SAP IFRS 18 webinar recordings (Feb/Mar 2026) for technical guidance | External webinar review - no transaction | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC | 1 | 2026-07-14 | 2026-07-15 | 2 | - | Not Started
1.9 | 1 | 1 - Design & Preparation | Review treasury compliance blog and check for TRM-specific notes | External blog / Support Portal search - no transaction | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC | 0.5 | 2026-07-14 | 2026-07-15 | 2 | - | Not Started
1.10 | 3 | 1 - Design & Preparation | Review treasury G/L accounts for IFRS 18 classification (interest, FX, dividends, fair value) | SM30 / SE16N on TRM accounting-derivation config (Account Assignment Reference) and affected G/L accounts | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC + Treasury | 2 | 2026-07-17 | 2026-07-21 | 5 | 1.1 | Not Started
1.11 | 1 | 1 - Design & Preparation | Use 1SG content package restructured Income Statement as reference blueprint for FSV design | Review of SAP Best Practice content (Scope Item 1SG) - reference only, no transaction in this landscape | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC | 1 | 2026-07-14 | 2026-07-16 | 3 | - | Not Started
2.1 | 4 | 2 - FSV Restructuring | Restructure ZHFM via OB58: add Operating/Investing/Financing nodes, two subtotal nodes, reassign P&L G/L accounts | OB58 (FSV = ZHFM, chart of accounts ZFRE) | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC | 5 | 2026-07-28 | 2026-08-03 | 7 | 1.2 | Not Started
2.2 | 5 | 2 - FSV Restructuring | Restructure ZCPL via OB58: apply IFRS 18 structure for controlling P&L | OB58 (FSV = ZCPL) | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC | 3 | 2026-08-04 | 2026-08-08 | 5 | 2.1 | Not Started
2.3 | 5 | 2 - FSV Restructuring | Restructure ZUKV via OB58: apply IFRS 18 categories preserving cost-of-sales classification | OB58 (FSV = ZUKV) | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC | 3 | 2026-08-04 | 2026-08-08 | 5 | 2.1 | Not Started
2.4 | 6 | 2 - FSV Restructuring | Unit test each FSV using standard financial statement reports (F.01 / RFBILA00) | F.01 / RFBILA00 (or S_ALR_87012284), one run per FSV | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC | 2 | 2026-08-09 | 2026-08-11 | 3 | 2.2 | Not Started
2.5 | 7 | 2 - FSV Restructuring | Peer review of FSV structures with group accounting | Review of OB58 output; meeting sign-off | 1 | IFRS Financial Statement Structure Definition | CONFIG | FC + Accounting | 1 | 2026-08-12 | 2026-08-12 | 1 | 2.4 | Not Started
3.1 | 8 | 3 - Configuration Updates | Update /FIT/FI_F_STRUCT table entries via SM30 - add new IFRS 18 P&L structure positions with attribute flags | SM30 on table /FIT/FI_F_STRUCT (new position codes, 21xxxx range) | 2 | G/L Account to Consolidation Structure Mapping | CONFIG | FC | 3 | 2026-08-15 | 2026-08-19 | 5 | 2.5 | Not Started
3.2 | 9 | 3 - Configuration Updates | Re-execute mapping program /FIT/FI_D_HFM_BIL_ZUORD_001 (ZHFMB0) with delete-and-regenerate | ZHFMB0 (program /FIT/FI_D_HFM_BIL_ZUORD_001); FSV=ZHFM, principle=GRUP, COA=ZFRE, delete flag=X | 2 | G/L Account to Consolidation Structure Mapping | CONFIG | FC | 0.5 | 2026-08-20 | 2026-08-22 | 3 | 3.1 | Not Started
3.3 | 10 | 3 - Configuration Updates | Validate regenerated /FIT/FI_F_HKONT mapping - verify all P&L accounts map to correct new positions, BS mappings intact | SE16N (display table /FIT/FI_F_HKONT) | 2 | G/L Account to Consolidation Structure Mapping | CONFIG | FC | 2 | 2026-08-23 | 2026-08-25 | 3 | 3.2 | Not Started
3.4 | 8 | 3 - Configuration Updates | Review all 510 entries in ZFI_IFRS16 mapping table - verify G/L accounts for depreciation (670xxx -> Operating) and interest (661xxx -> Financing) are correctly classified | ZFI_IFRS16_MAPPING / SM30 on table ZFI_IFRS16 | 7 | IFRS 16 Lease Accounting Data Loading | CONFIG | FC | 2 | 2026-08-15 | 2026-08-19 | 5 | 2.5 | Not Started
3.5 | 10 | 3 - Configuration Updates | Update ZFI_IFRS16 entries if chart of accounts changes or Tagetik introduces new codes | ZFI_IFRS16_MAPPING / SM30 on table ZFI_IFRS16 (field HKONT / TAGETIC_ACCOUNT) | 7 | IFRS 16 Lease Accounting Data Loading | CONFIG | FC | 1 | 2026-08-20 | 2026-08-22 | 3 | 3.4 | Not Started
3.6 | 8 | 3 - Configuration Updates | Activate Fiori apps F0708 and W0161 in Fiori Launchpad | /UI2/FLPD_CUST (Fiori Launchpad Designer) - activate F0708, W0161 | 4 | Financial Statement Data Export | INTERFACE | Basis/FC | 1 | 2026-08-15 | 2026-08-17 | 3 | 2.5 | Not Started
3.7 | 10 | 3 - Configuration Updates | Configure Fiori apps for IFRS FSVs (ZHFM, ZCPL, ZUKV) | F0708 / W0161 app configuration - bind default FSV parameters | 4 | Financial Statement Data Export | INTERFACE | FC | 1 | 2026-08-18 | 2026-08-19 | 2 | 3.6 | Not Started
3.8 | 8 | 3 - Configuration Updates | Apply SAP Note 3670330 child notes / corrections to CSD via SNOTE | SNOTE (Note Implementation) | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | Basis | 1 | 2026-08-15 | 2026-08-16 | 2 | 1.7 | Not Started
3.9 | 8 | 3 - Configuration Updates | Verify new semantic tags for Operating Profit and Profit before Financing and Income Tax | OB58 hierarchy node semantic-tag assignment; KPI framework config | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC | 1 | 2026-08-15 | 2026-08-16 | 2 | 1.7 | Not Started
4.1 | 8 | 4 - Development | Evaluate whether FG/FX document type exclusion is still a business requirement | Business decision workshop - no transaction | 5 | Income Statement Reporting (Cost of Sales) | REPORT | FC + Dev | 1 | 2026-08-15 | 2026-08-16 | 2 | 2.5 | Not Started
4.2 | 9 | 4 - Development | Create custom analytical query on I_JournalEntryItemCube via Custom Analytical Queries app (P&L filter + functional area classification) | Custom Analytical Queries app (Fiori) on CDS view I_JournalEntryItemCube | 5 | Income Statement Reporting (Cost of Sales) | REPORT | FC/Dev | 3 | 2026-08-17 | 2026-08-21 | 5 | 4.1 | Not Started
4.3 | 9 | 4 - Development | Optional: Create CDS view extension on I_JournalEntryItemCube for FG/FX filtering (if required) | ADT/Eclipse - DDLS extend view on I_JournalEntryItemCube; SE09/SE10 transport | 5 | Income Statement Reporting (Cost of Sales) | REPORT | Dev | 2 | 2026-08-17 | 2026-08-20 | 4 | 4.1 | Not Started
4.4 | 8 | 4 - Development | Update ZI_GLAcctBalanceCube CASE WHEN statement - replace hardcoded ZHFM hierarchy node IDs with new node IDs from restructured hierarchy | ADT/Eclipse - CDS view ZI_GLAcctBalanceCube source; SE09/SE10 transport | 6 | Working Capital Balance Sheet Reporting | ENHANCEMENT | Dev | 1 | 2026-08-15 | 2026-08-17 | 3 | 2.5 | Not Started
4.5 | 10 | 4 - Development | Verify ZC_WORKINGCAPITAL_Q001 downstream - confirm hierarchy filter binding still valid | ADT/Eclipse or RSRT - query ZC_WORKINGCAPITAL_Q001 filter binding | 6 | Working Capital Balance Sheet Reporting | ENHANCEMENT | Dev | 0.5 | 2026-08-18 | 2026-08-18 | 1 | 4.4 | Not Started
4.6 | 10 | 4 - Development | Evaluate SAC prototype views (ZP_WORKINGCAPITAL_ITEM etc.) for retirement | SAP Analytics Cloud review - no ABAP transaction | 6 | Working Capital Balance Sheet Reporting | ENHANCEMENT | Dev | 0.5 | 2026-08-18 | 2026-08-18 | 1 | 4.4 | Not Started
4.7 | 11 | 4 - Development | Unit test new P&L analytical query - compare output with ZC_PROFITANDLOSS_UKV for reference period | Run new query + ZC_PROFITANDLOSS_UKV via Fiori / Analysis for Office | 5 | Income Statement Reporting (Cost of Sales) | REPORT | FC | 2 | 2026-08-22 | 2026-08-25 | 4 | 4.2 | Not Started
4.8 | 11 | 4 - Development | Unit test working capital report - validate all 5 categories produce correct balances | Run working-capital report (Fiori app on ZC_WORKINGCAPITAL_Q001) | 6 | Working Capital Balance Sheet Reporting | ENHANCEMENT | FC | 1 | 2026-08-19 | 2026-08-20 | 2 | 4.4 | Not Started
5.1 | 11 | 5 - Interface Validation | Run HFM extraction in simulation mode (PX_SIMUL = 'X') via ZHFM01 | ZHFM01 (program /FIT/FI_D_HFM_INTF_001); parameter PX_SIMUL = 'X' | 3 | Financial Data Extraction for Group Consolidation | INTERFACE, CONFIG | FC | 1 | 2026-08-26 | 2026-08-29 | 4 | 3.3 | Not Started
5.2 | 12 | 5 - Interface Validation | Validate HFM output file format against HFM expected input - verify new structure positions appear correctly in aggregation pipeline (INTF1->4) | ZHFM10 (program /FIT/FI_D_HFM_INTF_010); AL11 / app server output review | 3 | Financial Data Extraction for Group Consolidation | INTERFACE, CONFIG | FC + HFM | 2 | 2026-08-30 | 2026-09-02 | 4 | 5.1 | Not Started
5.3 | 11 | 5 - Interface Validation | Verify /FIT/FI_F_KONSM and /FIT/FI_F_RMVCT entries are correct for new positions | SM30 on tables /FIT/FI_F_KONSM and /FIT/FI_F_RMVCT | 3 | Financial Data Extraction for Group Consolidation | INTERFACE, CONFIG | FC | 1 | 2026-08-26 | 2026-08-29 | 4 | 3.3 | Not Started
5.4 | 12 | 5 - Interface Validation | Test AMANA proxy parsing with restructured FSV output - verify positional parsing still works | ZFI_RFBILA00_DOWN (AMANA path); SE37 test of ZFI_AMANA_PROXY; SLG1 logs | 4 | Financial Statement Data Export | INTERFACE | FC | 1 | 2026-08-20 | 2026-08-22 | 3 | 3.7 | Not Started
5.5 | 13 | 5 - Interface Validation | Coordinate HFM-side configuration updates (new accounts/categories in HFM) | External system (Oracle HFM) - no SAP transaction | 3 | Financial Data Extraction for Group Consolidation | INTERFACE, CONFIG | HFM team | 3 | 2026-08-18 | 2026-09-06 | 20 | 1.4 | Not Started
5.6 | 13 | 5 - Interface Validation | Coordinate Tagetik account code alignment | External system (Tagetik) - no SAP transaction | 7 | IFRS 16 Lease Accounting Data Loading | CONFIG | Tagetik team | 2 | 2026-08-18 | 2026-09-06 | 20 | 1.5 | Not Started
5.7 | 13 | 5 - Interface Validation | Coordinate AMANA receiving system updates | External system (AMANA DMS) - no SAP transaction | 4 | Financial Statement Data Export | INTERFACE | AMANA team | 1 | 2026-08-18 | 2026-09-06 | 20 | 1.6 | Not Started
5.8 | 12 | 5 - Interface Validation | Validate Cash Flow Statement CDS view after note implementation | CDS view 2CCFICSHFLINDIFRS (Cash Flow Statement - Indirect Method for IFRS); test via report/app | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC | 0.5 | 2026-08-30 | 2026-08-31 | 2 | 3.8 | Not Started
5.9 | 11 | 5 - Interface Validation | Validate treasury valuation postings in restructured FSVs | Run TPM44/TPM1/TPM18 closing postings, then F.01/RFBILA00 to verify classification | SAPNOTE | SAP Notes & Treasury (added after reviewing Note 3670330 and the TRM open question) | CONFIG + ADVISORY | FC + Treasury | 1 | 2026-08-26 | 2026-08-29 | 4 | 1.10 | Not Started
6.1 | 14 | 6 - Integration Testing | End-to-end: FSV -> mapping regeneration -> HFM extraction -> file validation | Full chain: ZHFMB0 -> ZHFM01 -> ZHFM10; review final output file | 1->2->3 | GAP 1 -> GAP 2 -> GAP 3 | - | FC | 3 | 2026-09-03 | 2026-09-07 | 5 | 5.2 | Not Started
6.2 | 15 | 6 - Integration Testing | End-to-end: FSV -> P&L report with IFRS 18 categories and subtotals | Custom analytical query from 4.2 via Fiori / Analysis for Office | 1->5 | GAP 1 -> GAP 5 | - | FC | 1 | 2026-09-05 | 2026-09-07 | 3 | 4.7 | Not Started
6.3 | 15 | 6 - Integration Testing | End-to-end: FSV -> working capital report with updated hierarchy nodes | Working-capital report (ZC_WORKINGCAPITAL_Q001) | 1->6 | GAP 1 -> GAP 6 | - | FC | 1 | 2026-09-05 | 2026-09-07 | 3 | 4.7 | Not Started
6.4 | 15 | 6 - Integration Testing | End-to-end: IFRS 16 lease posting -> verify FSV classification (depreciation = Operating, interest = Financing) | Z_FI_I_LOAD_IFRS16 test run; F.01 / RFBILA00 classification check | 1->7 | GAP 1 -> GAP 7 | - | FC | 1 | 2026-09-05 | 2026-09-07 | 3 | 4.7 | Not Started
6.5 | 15 | 6 - Integration Testing | End-to-end: Financial statement export -> AMANA transfer | Full run of ZFI_RFBILA00_DOWN with AMANA export option | 1->4 | GAP 1 -> GAP 4 | - | FC | 1 | 2026-09-02 | 2026-09-04 | 3 | 5.4 | Not Started
6.6 | 15 | 6 - Integration Testing | Regression test: Shareholder reporting (FIT - no changes expected) | Run existing shareholder reports unchanged | - | N/A | - | FC | 0.5 | 2026-09-05 | 2026-09-07 | 3 | - | Not Started
6.7 | 16 | 6 - Integration Testing | Compare pre-IFRS 18 (XHFM/XCPL/XUKV) vs. post-IFRS 18 output for audit trail | OB58 (compare XHFM/XCPL/XUKV vs. ZHFM/ZCPL/ZUKV) + F.01 comparison | All | Cross-cutting | - | FC | 2 | 2026-09-05 | 2026-09-07 | 3 | - | Not Started
6.8 | 17 | 6 - Integration Testing | Defect resolution buffer | Fixes applied to the specific transaction/object where the defect was found | All | Cross-cutting | - | FC + Dev | 3 | 2026-09-08 | 2026-09-12 | 5 | 6.1 | Not Started
7.1 | 18 | 7 - QA Transport & UAT | Prepare transport requests (config + workbench) | SE09 / SE10 (Transport Organizer) - customizing + workbench requests | All | Cross-cutting | - | Dev/Basis | 1 | 2026-09-13 | 2026-09-15 | 3 | 6.8 | Not Started
7.2 | 19 | 7 - QA Transport & UAT | Execute transport CSD -> CSQ | STMS (Transport Management System) - CSD to CSQ | All | Cross-cutting | - | Basis | 0.5 | 2026-09-16 | 2026-09-16 | 1 | 7.1 | Not Started
7.3 | 20 | 7 - QA Transport & UAT | QA smoke testing - verify all 7 capabilities in CSQ | OB58, ZHFMB0, ZHFM01, ZHFM10, F0708/W0161, custom query, Z_FI_I_LOAD_IFRS16, ZFI_RFBILA00_DOWN | All | Cross-cutting | - | FC | 3 | 2026-09-17 | 2026-09-20 | 4 | 7.2 | Not Started
7.4 | 21 | 7 - QA Transport & UAT | User acceptance testing with business users (finance, controlling, consolidation) | Business users execute Fiori apps/reports listed in 7.3, in CSQ | All | Cross-cutting | - | Business + FC | 5 | 2026-09-21 | 2026-09-27 | 7 | 7.3 | Not Started
7.5 | 22 | 7 - QA Transport & UAT | Defect resolution and re-transport | Fixes in source object + SE09/SE10/STMS re-transport | All | Cross-cutting | - | FC + Dev | 3 | 2026-09-28 | 2026-10-02 | 5 | 7.4 | Not Started
7.6 | 23 | 7 - QA Transport & UAT | Re-test after fixes | Same transactions as 7.3 | All | Cross-cutting | - | FC | 2 | 2026-10-03 | 2026-10-06 | 4 | 7.5 | Not Started
8.1 | 24 | 8 - Production Go-Live | Execute transport CSQ -> CSP | STMS - CSQ to CSP | All | Cross-cutting | - | Basis | 0.5 | 2026-10-07 | 2026-10-08 | 2 | 7.6 | Not Started
8.2 | 25 | 8 - Production Go-Live | Production verification - run each capability and validate output | Same transactions as 7.3, executed in CSP | All | Cross-cutting | - | FC | 2 | 2026-10-09 | 2026-10-11 | 3 | 8.1 | Not Started
8.3 | 25 | 8 - Production Go-Live | Go-live communication to business users | Email/meeting - no transaction | All | Cross-cutting | - | PM | 0.5 | 2026-10-09 | 2026-10-09 | 1 | 8.1 | Not Started
8.4 | 26 | 8 - Production Go-Live | Hypercare support (2 weeks - monitor HFM extraction, reports, IFRS 16 postings) | SM37 (monitor jobs for ZHFM01/ZHFM10/Z_FI_I_LOAD_IFRS16), SLG1, ST22 | All | Cross-cutting | - | FC + Dev | 5 | 2026-10-12 | 2026-10-25 | 14 | 8.2 | Not Started
Total

## Effort Summary
Effort by Phase (updated Jul 14, 2026 - was 95 PD; +10 PD for SAP Note / Treasury activities)
Phase | Calendar Duration | Effort (PD)
1. Design & Preparation | 2 weeks | 20
2. FSV Restructuring | 3 weeks | 14
3. Configuration Updates | 2 weeks | 12.5
4. Development | 3 weeks | 11
5. Interface Validation | 3 weeks | 12.5
6. Integration Testing | 3.5 weeks | 12.5
7. QA Transport & UAT | 4 weeks | 14.5
8. Production Go-Live | 4 weeks | 8
Total | ~22 weeks | 105
Effort by Role
Role | Effort (PD) | % of Total
FI/CO Functional Consultant | 71.5 | 67%
ABAP Developer | 12 | 11%
Business Users (UAT) | 5 | 5%
Project Manager | 5 | 5%
External Teams (HFM, Tagetik, AMANA) | 6 | 6%
SAP Basis Administrator | 5 | 5%
Treasury Team | 1.5 | 1%
Total | 106 | 100%
Effort by GAP
GAP | Type | Effort (PD) | Notes
1. IFRS Financial Statement Structure Definition | CONFIG | 19 | Largest single item - 3 FSVs to restructure
2. G/L Account to Consolidation Structure Mapping | CONFIG | 9 | Table updates + mapping regeneration
3. Financial Data Extraction for Group Consolidation | INTERFACE + CONFIG | 10 | Includes HFM-side coordination
4. Financial Statement Data Export | INTERFACE | 7 | Fiori activation + AMANA testing
5. Income Statement Reporting (Cost of Sales) | REPORT | 9 | New analytical query + optional CDS extension
6. Working Capital Balance Sheet Reporting | ENHANCEMENT | 5 | CDS view node ID update
7. IFRS 16 Lease Accounting Data Loading | CONFIG | 6 | Mapping table review + Tagetik coordination
SAP Notes & Treasury (Activities 1.7-1.11, 3.8-3.9, 5.8-5.9) | CONFIG + ADVISORY | 10 | Not one of the original 7 GAPs - added after reviewing SAP Note 3670330 and the TRM open question
Cross-cutting (PM, defect resolution, transports, UAT, hypercare) | - | 30 | Shared across all GAPs
Total |  | 105
Effort by Work Type
Category | Effort (PD) | % of Total
Configuration / Customizing (OB58, SM30, table maintenance) | 30 | 29%
Development (CDS views, analytical queries) | 8 | 8%
Testing (unit, integration, QA, UAT) | 27 | 26%
External Coordination (HFM, Tagetik, AMANA) | 8 | 8%
Project Management & Go-Live | 14 | 13%
Defect Resolution Buffer | 8 | 8%
SAP Note Implementation & Treasury Verification | 10 | 10%
Total | 105 | 100%

## Milestones & Risks
Key Milestones
Date | Milestone
2026-07-18 | SAP Note 3670330 reviewed and child notes identified (new - precedes FSV restructuring)
2026-07-25 | Design complete - FSV node structures and HFM positions defined
2026-08-15 | FSV restructuring complete in CSD (ZHFM, ZCPL, ZUKV)
2026-09-05 | All configuration and development complete in CSD
2026-09-19 | Interface validation complete (HFM, AMANA)
2026-10-10 | Integration testing complete - all defects resolved
2026-10-13 | Transport to CSQ
2026-11-07 | UAT sign-off
2026-11-10 | Transport to CSP (Production)
2026-11-14 | Go-live verification complete
2026-12-05 | Hypercare ends
2027-01-01 | IFRS 18 effective - system fully operational
Risks
Risk | Impact | Mitigation
HFM-side changes delayed (external team dependency) | Blocks end-to-end validation of consolidation interface | Early kick-off in Phase 1; parallel workstream with HFM team starting Aug 18
Tagetik introduces new account codes for IFRS 18 | Additional mapping table entries needed in ZFI_IFRS16 | Coordinate with Tagetik team in Phase 1; buffer in Phase 3
FG/FX filtering required for P&L report | Adds CDS view extension development (2 extra PD) | Business decision in Phase 4 activity 4.1; effort already included as optional
ZHFM hierarchy node IDs change more extensively than expected | More CDS view updates needed in working capital report | Detailed node mapping in Phase 1 activity 1.2 identifies all affected nodes upfront
Transport conflicts in CSQ/CSP | Delays go-live | Dedicated transport request preparation; coordinate with other project teams
IFRS 18 updates IAS 7 - dividends paid to Investing, interest paid to Financing, interest received to Investing | Existing cash-flow reports/CDS views built on the old flexible classification may need updates | Add cash-flow classification check to Phase 2 unit testing (Activity 2.4); validate CDS view in Activity 5.8
SAP's own solution approach (Note 3670330) is still evolving and doesn't cover third-party (HFM) consolidation | Limited pre-built SAP support beyond the existing FSV/OB58 approach; HFM alignment remains fully this project's responsibility | Read Note 3696338 (Private Cloud/On-Premise) early in Phase 1 (Activity 1.7); consider a Customer Influence Request; re-check 3670330 periodically
R8: SAP Note 3670330 corrections not valid for the current release | Delays Activity 1.7/3.8; may require upgrade or manual backport | Check each note's Validity section during Activity 1.7; escalate to Basis/upgrade planning early if needed (Probability: Low)
R9: Treasury G/L accounts not correctly classified under IFRS 18 | Misstated Operating/Investing/Financing subtotals for treasury-driven P&L items, discovered late | Activities 1.10 and 5.9 explicitly verify this; treat confirmed TRM accounts like the ZFI_IFRS16 review in GAP 7 (Probability: Medium)
Assumptions
Assumption | Impact if Invalid
FSV restructuring design (G/L account -> IFRS 18 category mapping) agreed by group accounting | Phase 1 may need to be extended if not yet agreed
CSD development system available for configuration/development throughout the project | Delays configuration and development work if unavailable
No other major transports to CSQ/CSP conflict with this project's transport window | Could delay QA/production transports
HFM, Tagetik, and AMANA teams have capacity for their respective workstreams within the timeline | External dependency slippage is the largest schedule risk
Pre-IFRS 18 backup FSVs (XHFM, XCPL, XUKV) remain untouched for comparison/audit | Loss of audit trail / comparison baseline if backups are modified

## RACI Matrix
RACI Matrix (R = Responsible, A = Accountable, C = Consulted, I = Informed)
Activity / Capability | FI/CO Functional Consultant | ABAP Developer | SAP Basis | Project Manager | Group Accounting | HFM Team | Tagetik Team | AMANA Team | Business Users
1. FSV Restructuring (ZHFM, ZCPL, ZUKV) | R/A | - | - | C | I | - | - | -
2. G/L Account to HFM Structure Mapping | R/A | - | - | - | C | - | - | -
3. Financial Data Extraction for Consolidation | R/A | - | - | - | R | - | - | -
4. Financial Statement Data Export / AMANA | R/A | C | C | - | - | - | R | -
5. P&L Report by Cost of Sales Method | A | R | - | - | C | - | - | C
6. Working Capital Balance Sheet Report | A | R | - | - | - | - | - | C
7. IFRS 16 Lease Accounting Data Loading | R/A | - | - | - | - | - | R | -
Transport management (CSD/CSQ/CSP) | C | C | R/A | I | - | - | - | -
QA smoke testing | R/A | C | - | I | - | - | - | -
User acceptance testing (UAT) | C | - | - | A | C | - | - | R
Go-live communication & hypercare | R | R | C | A | I | I | I | I
Overall project coordination | C | C | C | R/A | I | I | I | I

## SAP Notes & References
Confirmed SAP Notes
Note | Title | Component | Validity / Status | Relevance / Action
3670330 | Financial Reporting according to IFRS 18 in SAP S/4HANA Cloud, SAP S/4HANA | FI-GL | v7, released 06.01.2026 | Central/umbrella note. Read first. Check Validity section and all child notes.
3694359 | How to Adopt IFRS 18 for Financial Reporting in S/4HANA Cloud Public Edition | FI-GL | Referenced by 3670330 | Low relevance - this landscape is not on Public Edition.
3696338 | Advisory Note on IFRS 18 Transition in S/4HANA Private Cloud, S/4HANA | FI-GL | Referenced by 3670330 | HIGH relevance - read this one next; matches this landscape's classic transactions/custom ABAP profile.
3700153 | Advisory Note on IFRS 18 Transition in SAP ERP | FI-GL | Referenced by 3670330 | Low relevance - only applicable if part of the landscape is still on classic ERP/ECC.
Child / Further Note Search Guide (me.sap.com/notes)
Search Term | Application Component | Why
IFRS 18 | FI-GL | Core GL changes for IFRS 18 presentation
IFRS 18 | FI-FIO-GL-HIE | Hierarchy/FSV enhancements for new categories
IFRS 18 | FI-FIO-GL-REP | Financial statement reporting updates
IFRS 18 | FI-FIO-GL-KPI | New semantic tags for Operating Profit, Profit before Financing
IFRS 18 | FIN-CS | Group Reporting / consolidation impacts
IFRS 18 | CA-GTF-CSC-EDO | Electronic disclosure / XBRL taxonomy updates
SAP Content Deliverables Tracker
Deliverable | Description | Status | Action / Activity Reference
SAP Note 3670330 | Central IFRS 18 note | Confirmed - see table above | Review + implement via SNOTE (Activities 1.7, 3.8)
Scope Item 1SG (Group Reporting reference content) | Extends/restructures Consolidation CoA and Income Statement; updates Cash Flow Statement starting point to Operating Profit | Confirmed via SAP+PwC blog (giulio_peretti, 2025-11-06) | Reference only - this landscape uses HFM, not SAP Group Reporting (Activity 1.11)
SAP IFRS 18 webinar series | Technical guidance sessions, Feb/Mar 2026 | Recordings likely available | Review recordings (Activity 1.8)
New semantic tags (Operating Profit, Profit before Financing and Income Tax) | KPI framework / Cash Flow Statement app support | Not yet confirmed for this release | Verify during Activity 3.9
Cash Flow Statement CDS view 2CCFICSHFLINDIFRS | Indirect method CFS for IFRS | Available in current release; update status not yet confirmed | Validate during Activity 5.8
External Source References
Blog Title | Author | Date | Platform | Key Takeaway
IFRS 18 Explained: What SAP S/4HANA Customers Need to Know Before 2027 | Praveenirrinki (SAP) | 2025-12-02 | SAP Community - Financial Management Blog Posts by SAP | General IFRS 18 background; confirms Note 3670330; links SAP webinar series (Feb/Mar 2026)
IFRS 18 and SAP S/4HANA Group Reporting: What It Means and How to Get Ahead | giulio_peretti, co-authored with PwC | 2025-11-06 | SAP Community - Financial Management Blog Posts by Members | Detailed SAP Group Reporting IFRS 18 capabilities; Scope Item 1SG update; PwC implementation approach
Unlocking the Value of SAP TRM for Corporate Treasury | mezeshan | 2026 (exact date not captured) | SAP Community - Financial Management Blog Posts by Members | General TRM tips; item #15 corroborates Note 3670330; links a treasury-specific IFRS 18 blog (URL truncated, not yet reviewed)
Treasury G/L Account Classification Checklist
Treasury Posting Type | IFRS 18 Category | Confirmation Status | Next Step
Interest expense on borrowings | Financing | Not confirmed - depends on whether SAP TRM is in use | Verify in Activity 1.10
Interest income on deposits | Investing | Not confirmed - depends on whether SAP TRM is in use | Verify in Activity 1.10
Dividend income | Investing | Not confirmed - depends on whether SAP TRM is in use | Verify in Activity 1.10
FX gains/losses on financial instruments | Depends on underlying instrument's category | Not confirmed - review operating vs. financing FX | Verify in Activity 1.10
Fair value gains/losses on derivatives | Depends on hedge designation | Not confirmed - review hedge accounting treatment | Verify in Activity 1.10
Depreciation of RoU assets (IFRS 16) | Operating | Confirmed in GAP 7 (accounts 670000/670002/670005/670006) | Already covered by Activity 3.4
Interest on lease liabilities (IFRS 16) | Financing | Confirmed in GAP 7 (accounts 661300/661302/661305/661306) | Already covered by Activity 3.4
Other lease expenses (IFRS 16) | To be verified | Confirmed in GAP 7 (accounts 671110-671306) | Already covered by Activity 3.4
Amortization (bond/security premium or discount) | Depends on instrument | Not confirmed - depends on whether SAP TRM is in use | Verify in Activity 1.10
Current portion reclassification (loans) | Balance sheet only - not a P&L category | N/A - reclassification is BS, not P&L | No P&L category action needed
Impairment losses/reversals (financial instruments) | Operating or Financing, depending on policy | Not confirmed - depends on whether SAP TRM is in use | Verify in Activity 1.10