## Slide 1
Demand Charter - 288 - IFRS 18
Titel
288 - IFRS 18
Demand
Manager
Enikő Baga
E2E /
Core Proc.
Finance – Accounting &
Financial Reporting (R2R)
Security
Classif.
Internal
Current Situation and Pain Points
Business Objectives and High-Level Demand Description
• IAS 1 today does not mandate P&L categories/subtotals → inconsistent presentation across entities and limited peer comparability.
• No formal governance for management-defined performance measures (MPMs) used in investor communications → audit/compliance risk.
• Chart of accounts and consolidation/reporting system not structured to auto-classify P&L lines into operating / investing / financing.
• Alternative performance measures produced via manual spreadsheets with limited audit trail.
• Inconsistent aggregation/disaggregation of line items across business units.
• No dedicated budget/resourcing yet assigned for IFRS 18 readiness.
• Achieve full IFRS 18 compliance before mandatory effective date (periods beginning ≥ 1 Jan 2027; comparatives from 1 Jan 2026).
• Gap assessment of chart of accounts, consolidation system and disclosure templates vs. the 3 new categories & 2 new subtotals.
• Define & govern Management-Defined Performance Measures (MPMs), incl. required reconciliation disclosures.
• Reconfigure P&L structure, CoA mapping and consolidation tool for native category/subtotal reporting.
• Update statutory templates, disclosure checklists and cash-flow reconciliation logic; train Finance/Controlling/IR.
• Run a parallel/dry-run cycle and align with external auditors on transition approach.
Benefits & Stakeholders & Allocations
Qualitative Benefits
• Full compliance with mandatory standard; avoids audit qualification.
• Improved comparability/transparency for investors via standardized subtotals.
• Stronger governance/audit trail over non-GAAP measures.
• Harmonized P&L supports statutory & management reporting.
• Reduced manual effort/error risk at close.
Quantitative Benefits
• Reduced manual closing/adjustment effort per cycle once automated (FTE-days TBD after design phase).
• Avoidance of one-off remediation costs (advisory, late changes, audit findings) from a rushed transition.
• Precise figures to be confirmed after gap assessment.
Stakeholders
• Group Finance / Corporate Accounting (owner)
• Group Controlling / FP&A
• Investor Relations
• Consolidation & Reporting Systems / IT
• Internal Audit & External Auditors
• Business Unit Controllers
Allocations Demand
Demand effort CIT (PD):
~40 PD (illustrative; IT/consolidation system config, CoA mapping, reports)
Demand effort BG (PD):
~25 PD (illustrative; gap assessment, MPM governance, policy, training)
INNOVATING TOGETHER